## Standard Violation
CRPO-160: Standards Volication
Company LBE Log/Register (Standard Violation)
Sl No. | LBE No. | Project | Location | Initiator | Issued Date | Title | Discipline | Subject | ACD | Response Date | Status | Closing Date
1 | 342 | CRPO160 | HAZIRA | Bhavesh Manani | 2026-07-15 | Unqualified Welder Used for Tack Welding | Mechanical | During fit-up inspection, joints P-1, P-2, and P-5 were root tacked by a welder not qualified for the required joint configuration. | 2026-07-20 | 16-07-2026, 29-07-2026 | Closed | 2026-07-29
2 | 350 | CRPO160 | HAZIRA | Bhavesh Manani | 2026-07-19 | Wet Condition Welding Observed | Mechanical | During surveillance, welding was performed under wet conditions on Joint No. P-50. | 2026-08-15 | 20-07-2026, 31-07-2026 | Closed | 2026-08-03
3 | 384 | CRPO160 | HAZIRA | Bhavesh Manani | 2026-07-30 | Bottom Beam Flange Mismatch Observed | Mechanical | During pre-weld inspection, a 5-7 mm mismatch was observed between the bottom beam flange and insert plate. | 2026-08-21 | 2026-07-31 | Open