## NCR Register
NON-CONFORMANCE REPORT (NCR) REGISTER
SN | NCR No. | Issue Date | NCR Catogory | NCR Submittal Date | Discipline | Area of Function | ACD | NCR Status | Description of Non-Conformance | Preventive Action Proposed
1 | DORRA-027 | 2026-07-03 | Minor | 2026-07-04 | Structure | Construction | 2026-08-02 | Closed | During the dimensional inspection of the West Boat Landing the to centre Leg of west boat landing distance not meeting with drawing requirement. as per drawing required.
2 | DORRA-028 | 2026-07-13 | Minor | 2026-07-14 | Structure | Construction | 2026-08-13 | Closed | during Fit-up inspection against Fit-up Request No.: it was observed that the long Seam orientation of Item No. 53 will be at 90° However, during Fit up inspection it was observed that, the long seam orientation was placed at 270°, where seam orientation.
3 | DORRA-029 | 2026-07-13 | Minor | 2026-07-14 | Structure | Construction | 2026-08-13 | Closed | during a Surveillance at Gantry-1, Yard-3,.Further investigation revealed that the fit-up inspection of the stiffener joints had not been accepted by QC&I prior to welding. Despite this, welding activities were carried out, bypassing the mandatory stage inspection requirements.This observation constitutes a violation of the approved ITP QM-0604-ITP-1303-Rev.Bstage inspection sequence, specifically Clause 3.5, which stipulates that Fit-Up Inspection is a HOLD Point for L&T QC&I and must be accepted before commencement of welding activities
4 | DORRA-030 | 2026-07-14 | Minor | 2026-07-15 | Structure | Construction | 2026-08-13 | Closed | during a surveillance inspection at Jacket GWHP-06, Yard-1, it was observed that partial root welding of the Barge Bumper TKY joints had been carried out without the required fit-up inspection being performed and accepted by KJO prior to the welding.
5 | DORRA-031 | 2026-07-17 | Minor | 2026-07-18 | Structure | Construction | 2026-08-17 | Open | During the review of the approved Shop Drawing, it was observed that in the King Post Arrangement Drawing, the component category of Item No. was incorrectly specified as Category C in the Bill of Material (BOM) for Jacket Nos. G4 and G6. Further investigation confirmed that the following items are required to be classified under Category B instead of Category C, as per Table-1.
6 | DORRA-032 | 2026-07-21 | Minor | 2026-07-22 | Structure | Design & Engineering | 2026-08-20 | Open | During the review of the approved Shop Drawing, it was observed that in the Pile GA Drawing, the component category of Item Stabbing Guide Material ASTM A572 Gr. 50 was incorrectly specified as Category B in the Bill of Material Further investigation confirmed that the following items are required to be classified under Category C instead of Category B, as Table-1
7 | DORRA-033 | 2026-07-22 | Minor | 2026-07-23 | Structure | Construction | 2026-08-22 | Open | during the final dimensional inspection at PS-4, Yard-3, it was observed that for the Bracing of C-4 of Jacket No. G7, the required linear dimensions at the CAN working point were 6040 mm and 6040 mm. However, the actual measured dimensions were found to be 6065 mm and 6052 mm, respectively. Further investigation confirmed that the horizontal bracings connected to the CAN joints are misaligned, resulting in deviation of the CAN working point dimensions from the approved drawing requirements.
8 | DORRA-034 | 2026-07-25 | Minor | 2026-07-28 | Structure | Construction | 2026-08-24 | Open | During a surveillance inspection conducted at it was observed in the shop fabrication area that a welding machine was found without a valid calibration.
9 | DORRA-035 | 2026-07-27 | Minor | 2026-07-28 | Structure | Construction | 2026-08-26 | Open | During fit-up inspection of Anode Joints at MODUL it was observed that the joints were offered for inspection without proper cleaning. Rust and foreign matter were found near the weld joint area.
10 | DORRA-036 | 2026-07-28 | Minor | 2026-07-30 | Structure | Construction | 2026-08-27 | Open | Material Identification Inspection was offered to the L&T QC Inspector on
11 | DORRA-037 | 2026-07-27 | Minor | 2026-07-30 | Mechanical | Construction | 2026-08-26 | Open | During weld visual inspection at GWHP-03, it has been observed that Welder numbers mentioned in the Matrix box and the welders offered in weld visual inspection request found mismatch.
12 | DORRA-038 | 2026-07-30 | Minor | 2026-07-31 | Structure | Construction | 2026-08-29 | Open | During weld visual inspection at it was observed that joint BY-192 had been offered for visual inspection before completion of the welding activity.