## Standard Violation
DORRA GAS WELL HEAD PLATFORM JACKETS PROJECT
Company LBE Log/Register (Standard Violation) CONTRACT NO. HQ002DP24
Sl No. | LBE No. | Project | Location | Initiator | Issued Date | Recived Date | Notification Title | Discipline | Subject | ACD | SAPMT/Contractor Response / Action Taken | Response Date | ACD Extended | Status | Closing Date | Contractor Closed by Initial | Repeat Violation | Catrgory | Escalated to SA NCR | Remark
33 | 33 | Dorra | Hazira | Subin Sukumaran | 2026-07-04 | 2026-07-07 | Non-Compliance with Sch-Q Requiremts for shop / field welding inspection personnel. | Mechanical | On 04-July-2026, at MFF yard # 3, during routine surveillance, the Project Inspection Representative observed that more than 70 welders were engaged in ongoing shop/field fabrication activities (PS's, Gantry's & open yard). However, these activities were being monitored by only four (4) inspectors. This is in violation of the requirements specified in Sch Q, Att VI - Construction Phase Quality personnel Requirements, which states that for field welding there shall be one (1) full time Inspector for every ten (10) welders, and for shop welding there shall be one (1) full time Inspector for every fifteen (15) welders. Further verification of the store issuance slips and the welder records revealed that the list of welders submitted to KJO on 04-July-2026 was not up to date, as several welders actively involved in fabrication were not included in the submitted list. The Contractor is therefore advised through PMT to comply with the requirements of Sch-Q by providing adequate quality inspection personnel and maintaining accurate updated welder records. Failure to comply may result in further escalation in accordance with SAEP-381. | 2026-08-03 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. 'Root Cause Analysis: Due to the emergency leave of multiple approved Welding QC Inspectors, the CONTRACTOR was unable to maintain the required quality inspection manpower at the Open Yard (Yard-3) as stipulated in Schedule Q. However, the overall project inspection manpower requirement, as per Schedule Q, was maintained across the project. Corrective Action: The CONTRACTOR will ensure that overall project inspection manpower requirement is maintained in compliance with Schedule Q requirements. Additionally, quality inspectors will be deployed and redistributed among all work locations (Yards) based on inspection workload and activity priorities to always ensure adequate inspection coverage. | 2026-07-06 |  | Closed | 2026-07-24 | Abhinav Patel | No | Minor
34 | 34 | Dorra | Hazira | Subin Sukumaran | 2026-07-04 | 2026-07-07 | Welder identification not indicated on weld joint | Mechanical | On 6 July 2026, at L&T MFF Yard 3, during routine surveillance, the Project Inspection Representative observed the welder identification (Welder ID/Symbol) was missing on the T-K-Y Joint in the weld matrix table during in-process welding. Welding was being carried out by Welder ID No.: BT13 using the FCAW process for GWHP05 - Dwg No. S-0604-KA-187927-E-MFF-SHT-01-Rev.00, Joint No.: TK18. Hence it is a clear violation of the requirements of SAEP-1160, Paragraph 6.3.17, (Welder identification) which states "Indicate approved welder or welders by identification symbol(s) who are welding the joint". The Contractor is therefore advised through PMT to submit the root cause analysis along with corrective actions to prevent re-occurrence of this nonconformance. | 2026-08-05 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. 'Root Cause Analysis (RCA): The welder started welding without marking the welder ID number on the TKY joint. This happened due to oversight and failure to follow the welding identification procedure. Correction: The welder ID number was immediately marked on the concerned TKY joint. The weld was then checked and confirmed by the inspection team as per the applicable procedure. Corrective Action: A Tool Box Talk (TBT) was conducted for all welders to remind them of the requirement to mark their welder ID number before starting any welding activity. The welding identification procedure was explained again, and all welders were instructed to follow it strictly to avoid recurrence of this issue. 'CONTRACTOR confirmed that, the welder ID number was immediately marked on the concerned TKY joint (TK-18), Post weld visual Inspection carried out & accepted via RFI No: DORRA7J-MFF-M-03094. A Toolbox Talk (TBT) was conducted for all welders to create awareness. | 2026-07-06 |  | Closed | 2026-07-24 | Abhinav Patel | No | Minor
35 | 35 | Dorra | Hazira | Dyal Kandasami | 2026-07-09 | 2026-07-10 | Construction phase quality personnel requirements | Mechanical | On 09-July-2026, during night shift surveillance at the MFF-1, MFF-2, MFF-3 & MFF-4 Fabrication yards, the Company inspection representative observed that the contractor had not deputed a project approved QC supervisor to provide night shift coverage (19:00 to 04:00), while welding & Fabrication activities were ongoing across all four yard locations. During the surveillance, 4 project approved QC inspectors were deployed to monitor welding & fabrication activities; however, no project-approved QC supervisor was available at the MFF fabrication yards. This is in violation of the requirements of Schedule Q, Attachment VI, paragraph 2.2 and Exhibit 1 - Construction phase quality personnel requirements. | 2026-08-09 | With reference to the Weekly Quality Meeting (WQM-20) dated 09-07-2026, MOM Sr. No. 27, the Contractor informed the Company & agreed that a QC Supervisor will be deployed for night-shift welding activity monitoring form 14-July-2026 onwards. In view this contractor request Company to withdraw this Standard Violation and close the observation. | 2026-07-11 |  | Withdrawn |  | Abhinav Patel | No | Minor
36 | 36 | Dorra | Hazira | Sahayaraj Stalin | 2026-07-09 | 2026-07-10 | Incorrect Welder Symbol & Missing Weld Identification | Mechanical | During Site Surveillance at MFF1 the following observations were identified: The welder symbol was not marked in the Weld Matrix for the completed joint. Details: Jacket No: GTWHP04, Joint No F6, DWG NO: 8-0604-KA-187811-D-MFF-Sh-1. The contractor recorded an incorrect Welder symbol in the Weld Matrix. The mentioned Welder is not available in the approved project welder list. Details: Jacket No: GTWHP-04, Joint No 5, DWG NO: 8-0604-KA-187811-D-MFF-Sh-1. These observations are non-compliance with SAES-W-013, Para 14.1. | 2026-07-19 | Root Cause Analysis (RCA): Drawing No:- 8-0604-KA-187811-D-MFF-001. The qualified welder (CT66) commenced welding at Joint T-6 without marking his welder identification number on the J-tube joint. Additionally, for Joint T-5, the welder identification was marked as CTW, making the welder ID difficult to read and resulting in misinterpretation instead of CT66. This happened due to failure of welder (CT66) to follow the welding identification requirement and same thing was oversight by production team. Correction: The correct welder identification number (CT66) was immediately marked on the concerned joints.In addition, MPT will be performed on Joints T-5 and T-6 to verify weld integrity. Corrective Action: A Toolbox Talk (TBT) will be conducted for all welders to reinforce the requirement of marking their welder identification number on the joint prior to commencing any welding activity. A warning letter will be issued to Welder CT66 for non-compliance with the welder identification and traceability requirements before the start of welding. 'The correct welder identification number (CT66) was immediately marked on the concerned joints. Weld visual cleared through the respective RFI no:DORRA 7J -MFF-M-3392 . Additionally, MPT was performed on Joints T-5 and T-6 to verify the integrity of the welds. A Quality awarness session conducted for all welders along with excucation team to reinforce the requirement of marking of welder identification number on the joint prior to commencing any welding activity. A warning letter issued to Welder CT66 for non-compliance with the welder identification and traceability requirements before the start of welding. | 2026-07-11 |  | Closed | 2026-07-18 | Abhinav Patel | Yes | Moderate
37 | 37 | Dorra | Hazira | Gowthaman Janakiraman | 2026-07-10 | 2026-07-11 | welding consumables | Mechanical | During the surveillance at the MFF-4 welding consumables store, the following non-conformities were observed: 1) FCAW and SAW consumable coils were found to be rusted and contaminated. The rusted FCAW consumable had been issued and used for welding. 2) The batch number of the issued FCAW consumable did not match the actual batch number of the consumable available in the store, indicating a traceability failure. The above observations are not in compliance with the requirements of SAES-W-013, Appendix 2 and QM-0609-PL-1037, Clause 6.5.10. | 2026-08-08 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. Point No. 1 Root Cause:Rusting spool was identified at store. While investigating it was identified that at end of the shift, balance spool of FCAW and SAW return from site may contain some rain drop on wire while putting into the box. Corrective Action:Rusted spool identified and discarded. Return spool from site need to properly check before taking back. Toolbox talk will be given to store person and helpers for taking proper care of welding consumable while use and return to consumable store. To give confidence on consumable control system, contractor will perform NDT of return spool welder joint. Point No. 2 Root Cause:On 08/07/2026, a fresh FCAW spool from batch U80720 was issued to a CV51 welder, who returned approximately 11 kg of wire to the store at the end of the shift. The following day, while reissuing the returned spool, the storekeeper inadvertently scanned a different batch number (U80652) instead of the actual spool batch (U80720). Both U80652 and U80720 are approved for the Dorra Project and comply with all project quality requirements. Corrective Action:The storekeeper has been instructed to verify spool batch numbers carefully before issuance and to ensure that the correct batch is scanned and recorded. 'The identified rusted spool was discarded, and controls have been reinforced to ensure all return spools are properly inspected before being accepted into the consumable store. A toolbox talk was conducted for store personnel and helpers on the proper handling and storage of welding consumables. The contractor performed NDT on the welded joints made using the returned spool, with acceptable results, confirming the effectiveness of the consumable control system. Additionally, the storekeeper has been instructed to verify spool batch numbers carefully and ensure correct batch scanning and recording during issuance to prevent recurrence of similar issues. | 2026-07-13 |  | Closed | 2026-08-07 | Abhinav Patel | No | Minor
38 | 38 | Dorra | Hazira | SANJEEV KUMAR | 2026-07-11 | 2026-07-13 | finish coat surface was observed to have paint drips, sagging, dry spray, foreign matter and missed coating areas | Coating | On 11 July 2026 at L&T MFF Hazira Yard-2, during the final Top Coat inspection of ROW-1 Jacket No - GWHP-07 (Partial Area) coated with APCS-11C, the finish coat surface was observed to have paint drips, sagging, dry spray, foreign matter and missed coating areas. This is a clear violation of SAES-H-004, Clause 9.4.5.2 and 9.4.5.3, which state that the Top Coat shall be generally free from application related defects such as sags, drips, dry spray, foreign matter and shall have a uniform appearance. The contractor is advised to rectify all identified defects and ensure that the entire coated surface complies with the requirements of SAES-H-004 before submitting the area for the final inspection RFI. Adequate internal quality checks shall be carried out to verify compliance prior to requesting inspection. | 2026-07-26 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. Root Cause Analysis: The missed coating on anode brackets, along with localized dry spray and paint drip, was not identified during the Contractor's internal visual inspection prior to offering the item for COMPANY inspection. The affected areas were isolated in nature, while the remaining coated surfaces were found to be in compliance with the applicable project specification requirements. Correction: The CONTRACTOR will rectify the identified deficiencies in accordance with the approved coating procedure and project specifications. Upon completion of the rectification work, the item will be re-offered to COMPANY for inspection. Corrective Action: The CONTRACTOR will strengthen the coating inspection process by ensuring a thorough final visual inspection is conducted before offering items for COMPANY inspection. 'The affected area has been rectified and offered for CPY inspection against RFI No: DORRA 7J-MFF-H-00134, which has been accepted by KJO. Furthermore, an awareness session has been conducted to prevent further escalations. | 2026-07-14 |  | Closed | 2026-07-24 | Abhinav Patel | No | Minor
39 | 39 | Dorra | Hazira | Sahayaraj Stalin | 2026-07-13 | 2026-07-15 | Inspection coverage and Weld Identification | Mechanical | On 13-07-2026, during the Post-Weld visual inspection at L&T MFF yard / shop-1 for jacket GIWHP-06, the inspection representative rejected RFI no: DORRA-7J-MFF-M-03119. The rejection was due to Welder No: BU96, and mismatch between the actual weld matrix and the contractor's approved weld visual inspection reports DORRA-JACKET-W6-WV-667 & 668. (In reports: Welder NO: BD29 In the actual weld matrix: BU96, BC48 & BD29) This indicates that the contractor failed to perform the required first level inspection, violated SAEP 1150, para 9.6.1 DWG No:- 8-0604-HA-188102-F-MFF-Sh1-Rev F. observed joints:- P188, P189, P190, P192, P193, P194, P94, P95, TP-23, P96, TP-19, TP-20, TP-21, TP-22, P91, P92 & TP-24. | 2026-07-24 | Root Cause Analysis (RCA): RFI NO: DORRA 7J-MFF-M-03119, Drawing No:- 8-0604-KA-188102-F-MFF-Sh-1. During the visual inspection stage, the QC Inspector failed to verify the welder matrix against the weld visual inspection request. Consequently, the discrepancy in the welder matrix remained undetected and was subsequently identified by the PID Inspector during the RFI inspection. Correction: The weld visual inspection shall be re-offered under a new RFI with the correct welder identification number reflected in the welder matrix. Corrective Action: The Welding Inspector has been strictly instructed to re-verify the welder matrix against the relevant welding records prior to offering any RFI for PID inspection. Additionally, heightened vigilance shall be maintained to ensure such discrepancies do not recur in future inspections. 'The new Weld Visual Inspection RFI No: DORRA 7J -MFF-M-03562 was cleared by PID, with the correct welder identification number reflected in the welder matrix. During an awareness session, the Welding Inspectors were instructed to re-verify the welder matrix against the applicable welding records prior to offering any RFI for PID inspection. Additionally, enhanced vigilance shall be maintained to ensure that such discrepancies do not recur in future inspections. | 2026-07-16 |  | Closed | 2026-07-24 | Abhinav Patel | Yes | Moderate
40 | 40 | Dorra | Hazira | Sahayaraj Stalin | 2026-07-15 | 2026-07-16 | Installation of Material 2" Nipple (Surplus Material) without Material Receiving Inspection (MRI) | Mechanical | It has been observed that company inspection representative identified that Non-Inspected Material / Surplus Material (2" Nipples), has been installed on the jacket GIWHP07, GIWHP06, GIWHP05, GIWHP04, GIWHP03, and GIWHP02 prior to the completion of the required Material Receiving Inspection and company approval. This violate the requirement of company approved Inspection and test plan (ITP) QM-0604-ITP-1303, Rev-00B Activity 2.1 and contractor Material Management procedure QM-0604-PI-1305 para 6.2 | 2026-08-15 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. 'Root Cause:Based on practices followed in previous ARAMCO projects, where 2-inch pipe nipples and caps used as grout ports were considered temporary, non-permanent items and were installed without COMPANY approval or inspection, the CONTRACTOR incorrectly assumed similar requirements would apply to the Dorra Project. Consequently, the items were installed based on internal L&T inspection only, without obtaining prior KJO approval and KJO IND inspection. Corrective Action:1.A formal approval request was submitted to the Company through Letter No. LT-KJO-PKG1-L-0447-2 dated 15 July 2026 for the transfer and utilization of 2-inch pipe nipples and 2-inch caps from the CRPO 121 and 30 Jacket Project for grout port applications in the Dorra Project. 2.Going forward, the CONTRACTOR shall obtain prior written approval from Company/KJO and ensure KJO IND inspection and acceptance before transferring, installing, or utilizing any materials from other projects, irrespective of the component category. The requirement has been communicated to all concerned departments to ensure compliance and prevent recurrence. | 2026-07-18 |  | Open |  | Abhinav Patel | Yes | Minor
41 | 41 | Dorra | Hazira | Subin Sukumaran | 2026-07-18 | 2026-07-18 | RFI Rejected - Nonconformance in stiffener installation for Conductor Cone | Mechanical | On 18 July 2026, at L&T MFF Yard #3, Gantry No 3, during the visual inspection of the welded stiffener joints for the Conductor Cone for the Conductor Guide Facility - CGF03 of Jacket No: GWHP-04 belong to the RFI No: DORRA-7J-MFF-M-03407, the Project Inspection Representative observed that the stiffner installed and welded to the Cone and tubular section at Joint Nos: P-290, P-298 & P-300 were of incorrect dimensions. As per Drawing No: 8-0604-KA-187F06-D-MFF-SH001, Rev. 00C, the required width of stiffner Item No: CGF106 is 175mm. However, a stiffner with a width 165mm was installed resulting in a mismatch with the approved profile geometry. This constitutes a clear Non Conformance with the approved drawing requirements specified in Drawing No: 8-0604-KA-187F06-D-MFF-SH001-Rev.00C. The Contractor is therefore advised, through PMT to submit the root cause analysis, along with corrective actions to prevent reoccurrence of this non conformance. | 2026-09-17 | CONTRACTOR acknowledged COMPANY's Standard Violation. 'Root Cause Analysis (RCA) During weld visual inspection, the grinder inadvertently performed flush grinding up to the 45° notch area. As a result, the stiffener width was reduced and measured at 165 mm instead of the required 178 mm. Correction The existing welded stiffener will be completely removed. Surface NDT will be carried out after removal, and a new stiffener will be installed in accordance with the approved drawing and in compliance with the applicable ITP requirements. Corrective Action A toolbox talk and awareness session will be conducted for the entire fabrication team to reinforce drawing requirements, dimensional control, and proper grinding practices to prevent recurrence of similar issues. '1.The existing welded stiffener removed completely and subsequently Surface NDT (MPT) had been carried and found satisfactory (Report No: 108194). 2.A new stiffener installed in accordance with the approved drawing and further Re-Fit-up and Weld visual inspection has been performed & accepted via RFI No: DORRA7J-MFF-M-03517. 3.A toolbox talk and awareness session conducted (Dated: 6th Aug 2026) to reinforced drawing requirements, dimensional control, and proper grinding practices to prevent recurrence of similar issues. | 2026-07-20 |  | Closed | 2026-08-07 | Abhinav Patel | No | Minor
42 | 42 | Dorra | Hazira | SANJEEV KUMAR | 2026-07-18 | 2026-07-20 | finish coat surface was observed to have paint drips, sagging, dry spray, foreign matter and missed coating areas | Coating | On 18 July 2026 at L&T MFF-2 Hazira yard-2, During the Final Top Coat Inspection of Row-1 Jacket No-GNHP-01 (Partial Area) Coated with APCS-19C, the finish coat surface was found to contain pinholes in paint touch up areas, dust inclusions and foreign matter embedded in the top coat finish. This condition constitutes a non conformance with SAES-H-004, specifically • Clause 9.4.5.3- Which requires the finish coat to be generally free from application related defects. • Clause 9.4.5.1 - Which requires the completed top coat to exhibit a uniform appearance and be free from defects such as sags, drips, dry spray, pinholes, dust inclusions foreign matter and other application Related imperfections. The contractor is instructed to rectify all Indentified defects by carrying out the necessary surface preparation and recoating, as required to achieve full compliance with the specification. The entire coated surface shall be throughly inspected through the contractor's internal quality control process to verify compliance with SAES-H-004 prior to resubmitting the area for the final Inspection Request for Inspection (RFI). | 2026-08-03 | CONTRACTOR acknowledged COMPANY's Standard Violation. Root Cause Analysis: Pinholes, foreign matter inclusion were observed on freshly touch up area, which was missed to verify by Contractor's internal visual inspection prior to offering for COMPANY inspection. The affected areas were limited to fresh paint touch up area, while the remaining coated surfaces were found to be in compliance with the applicable project specification requirements. Correction: The CONTRACTOR will rectify the identified deficiencies in accordance with the approved coating procedure and project specifications. Upon completion of the rectification work, the item will be re-offered to COMPANY for inspection. Corrective Action: The CONTRACTOR will strengthen the coating inspection process by ensuring a thorough final visual inspection is conducted before offering items for COMPANY inspection. 'The affected area has been rectified and offered for CPY inspection against RFI No: DORRA 7J-MFF-H-00157, which has been accepted by KJO. Furthermore, an awareness session has been conducted to prevent further escalations. | 2026-07-20 |  | Closed | 2026-08-03 | Abhinav Patel | Yes | Minor
43 | 43 | Dorra | Hazira | Abdul Raheman Motiwala | 2026-07-18 | 2026-07-20 | IFC Drawing requirement | Mechanical | During Routine surveillance inspection at MFF-4 for the west boat landing of GWHP-04 Jacket, it was observed that minimum distance between adjacent completed weld joints at joint No. TK-128 was not maintained in accordance with IFC Drawing No. 8-0604-KA-187773-D-MFF-Sh 2 Rev. 00C. The Drawing specifies a spacing of 75\text{ mm} between weld joints; however the actual measured distance was found to be 20\text{ mm}. This violates the IFC Drawing requirement. | 2026-08-19 | The requirement to maintain a minimum 75 mm distance between adjacent TKY joints, as specified in IFC Drawing No. 8-0604-KA-187773-D-MFF-SH02 Rev. 00C, is applicable during the fit-up stage prior to welding. Further to that heat affected zone of both the weld does not overlap and joint belongs to Component category C to C hence no impact on structural integrity. Also, as per API-RP-2A cl. 7.2.5 “The minimum nominal gap between adjacent braces, whether in- or out-of-plane, is 50 mm (2 in.). Care should be taken to ensure that overlap of welds at the toes of the joint is avoided. “ Based on the above justification, contractor request company to withdraw the LBE- 43. | 2026-07-22 |  | Closed | 2026-08-06 | Abhinav Patel | No | Minor
44 | 44 | Dorra | Hazira | Abdul Raheman Motiwala | 2026-07-20 | 2026-07-21 | the applicable WPS was not identified in the Weld Matrix | Mechanical | During Surveillance at Yard-4 on 20/07/2025 for West Boat Landing of Jacket GWHP06, Drawing No. 8-0504-KA-188023-F-MFF-SH2, Joint No. TK-107, the applicable WPS was not identified in the Weld Matrix. Furthermore, welding of the joint had been completed up to the capping pass without the weld matrix specifying the approved WPS to be used. This condition is not in compliance with SAEP-1150 clause 6.3.18. | 2026-07-27 | Root Cause: The non-conformance occurred because the WPS number was missed to write in the weld matrix by welding forman. same was overlooked by the welders prior to start of welding. Correction: •The weld matrix was immediately reviewed and updated with the correct approved WPS number. •Warning letter issued to concern welder no. BG90, BP75 and T87. Corrective action: •Toolbox talk will be conducted to welding foremen and welders to reinforce the requirement for verifying and maintaining the correct WPS details in the weld matrix before start welding activities. •Surveillance of weld matrix will be increased to ensure that WPS no.to be available during the welding operation. 'The weld matrix has been updated with the correct approved WPS number. Warning letters have been issued to welders BG90, BP75, and T87. Additionally, a toolbox talk has been conducted with welding foremen and welders to emphasize the importance of verifying and maintaining accurate WPS details in the weld matrix prior to starting welding activities. | 2026-07-22 |  | Closed | 2026-07-27 | Abhinav Patel | No | Minor
45 | 45 | Dorra | Hazira | Sahayaraj Stalin | 2026-07-21 | 2026-07-21 | Verified welder assigned for production welding | Mechanical | during site surveillance at L&T MFF-1, it was observed that Welder BR54, who was not qualified for production welding, had performed welding on joint No. P-2/P-10 referring DWG No. 8-0601-KA-187776-D-MFF-Sh-1 for jacket NO: GWHP-04. It was also observed that the contractor had planned to assign the same welder to perform welding on some other joints like P-4. The welder had not completed the required 1st three performance qualification joints and was therefore not qualified to perform production welding. | 2026-08-20 | Root Cause Analysis (RCA): The welder (BR-54), who was undergoing SMAW (6G) performance qualification, had completed three initial test joints, of which two were accepted and one required repair. As per the qualification requirements, the same welder subsequently completed two penalty test joints; however, the weld visual inspection and NDT were still pending. Due to a communication and verification lapse, the Welding Foreman failed to review the pending JCC qualification status and mistakenly deployed the welder for production welding on Joint No. P-2 & P-10 (Fillet weld of closer plate) as per Drawing No. 8-0601-KA-187776-D-MFF-Sh-1. Consequently, welding was carried out without verifying the successful completion and acceptance of the required welder qualification tests, resulting in the welder performing production welding prior to obtaining the necessary qualification approval. Correction: The welder was immediately removed from production welding activities.Weld metal deposited by the welder on the affected joint will be completely ground off and Magnetic Particle Testing (MPT) shall be performed on the ground area to ensure that no defects remain. Corrective Action: Mandatory verification of JCC and welder qualification status shall be implemented prior to deployment of any welder for production welding activities. Awareness training shall be conducted for Welding Foremen and Supervisors on welder qualification control requirements, responsibilities, and verification procedures before assigning welders to production work. Additionally, heightened vigilance shall be maintained to ensure such discrepancies do not recur in future inspections. 'Weld metal deposited by the welder on the affected joint was completely ground off and NDT (MPT) was performed on the ground area to ensure that no defects remained. Awareness training was conducted for Welding Foremen and Supervisors on welder qualification control requirements, roles and responsibilities and verification procedures prior to assigning welders to production welding activities. Additionally, increased vigilance shall be maintained to ensure that such discrepancies do not recur in future. | 2026-07-22 |  | Closed | 2026-08-06 | Abhinav Patel | No | Minor
46 | 46 | Dorra | Hazira | Sahayaraj Stalin | 2026-07-25 | 2026-07-27 | Adjacent weld beads joints were not properly staggered. | Mechanical | On 25-July-2026, during site surveillance at L&T MFF fabrication yard #1 for Jacket, GWHP-06, the Company Inspection Representative observed the following non-conformances. Observations: Adjacent weld beads at joints P-5, P-244, P-246, and P72/72 (DWG NO: 8-0604-RA-188/02-F-MFF-Sh-01) were not properly staggered. Welder NOs: BJ43, BU86, B154 WPS: MFF-SA-WPS-STR-56 This violates SAES-W-013 para 10.14. Weld completion dates were not recorded for critical TKY joints TK-9 (DWG NO: 8-0604-RA-188/02-F-MFF-Sh-01) and TK-12 (DWG NO: 8-0604-RA-188/026-F-MFF-Sh-01), despite repeated instructions. This violates QM-0604-PL-1017, para 5.1(d) and prevents verification of the mandatory 48-hours delay before NDT. Two SMAW welders were used on a single joint, but the weld portion completed by each welder was not identified, resulting in inadequate welder traceability in case of an NDT rejection. | 2026-08-25 | CONTRACTOR acknowledged COMPANY's Standard Violation. CONTRACTOR will response with root cause, correction and corrective action. 'Root Cause Analysis (RCA): 1) The qualified welders (BJ43, BU86, and BI54) performing FCAW welding were not adequately aware of the requirement for proper staggering of adjacent weld beads as per approved welding procedure. In addition, the Welding foreman and Execution team failed to identify and rectify the deviation during in-process monitoring. 2) The execution team and Welding Foreman failed to record the weld completion date in the weld matrix for the concerned critical TKY joints. Although the weld completion date and time were maintained in the system for monitoring the mandatory 48-hour holding period prior to NDT, the required manual entry in the weld matrix was overlooked. 3) The Execution team and Welding Foreman failed to ensure proper identification and marking of the weld portions completed by each SMAW welder on the joint. While the welder identification numbers were recorded in the weld matrix, the specific weld segments welded by individual welders were not marked. Correction: 1) The adjacent weld bead start and stop locations at joints P-5, P-244, P-246, and P72/72 (DWG No. 8-0604-KA-188102-F-MFF-001) were immediately rectified by grinding and re-profiling the weld beads to ensure proper staggering in accordance with the applicable welding requirements.NDT will be performed after the weld completion. 2) The weld completion date was immediately recorded in the weld matrix for the critical TKY joints TK-9 (DWG No. 8-0604-KA-188102-F-MFF-001) and TK-12 (DWG No. 8-0604-KA-188026-F-MFF-001) 3)The specific weld segments completed by each SMAW welder on the concerned joint were immediately identified and marked Corrective Action: The concerned welders, Welding Foremen, Welding Inspectors, and execution personnel were sensitized through a quality awareness session on the importance of: Maintaining proper staggering of adjacent weld beads, record the weld completion date in the weld matrix for the concerned critical TKY joints and Properly identifying and marking the specific weld portions completed by each welder on a joint. Additionally, all Welding Foremen and Welding Inspectors have been instructed to verify these requirements during routine surveillance. Heightened vigilance and periodic monitoring shall be maintained to ensure continued compliance and prevent recurrence of similar discrepancies in future inspections. | 2026-07-28 |  | Open |  | Abhinav Patel | Yes | Minor
47 | 47 | Dorra | Hazira | Dyal Kandasami | 2026-07-28 | 2026-07-28 | Requirements of the approved procedure of Heat Straightening | Mechanical | On 28-July- 2026, during surveillance of Jacket GWHP01 – South Boat Landing at MFF-4 Fabrication Yard, the Company Inspection representative observed that the contractor carried out Heat Straightening on the Rub Strip without informing the Company prior to commencing the activity. The Contractor thereby failed to comply with the requirements of the approved procedure of Heat Straightening (DOC No: QM-0604-PL-1330), Para 8 & 9. Drawing No: 8-0604-KA-187420-A-MFF, Sh-1. Joint No: P-229, 230 & 231. | 2026-08-28 | Root Cause: The Fabrication Supervisor, incorrectly interpreted that notification to KJO was not required for heat straightening activities on Category D components. Correction: 1.Conduct visual inspection of the affected area for any surface defects or abnormalities. 2.Perform surface NDT to verify the absence of defects. 3.Carry out hardness testing at the affected location to confirm material integrity. Corrective Actions: 1.QCS (Welding), Mr. Krunal, conducted an awareness session for all Fabrication Supervisors emphasizing the mandatory RFI requirement and compulsory witness of heat straightening activities by KJO and L&T Inspectors. 2.Develop and implement a Mandatory Quality Requirements List for focused compliance assessment and monitoring across all KJO Project fabrication activities. | 2026-07-30 |  | Open |  | Abhinav Patel | No | Minor